## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Unity Cloud Build | Unity changes charging system, CloudBuild could cost (more) money | 2% | 3 | 0.06 | Pay the money (or switch CI-Tool) | Patrick
Sickness | One of the Teammembers gets sick | 10% | 1 | 0.1 | Buffer time | Patrick
Collision between Exams and Project | Some Exams might be earlier | 30% | 4 | 1.2 | Buffer time | Patrick
Inexperience with utilized technologies | Some technologies are completely new to our team, which could cause delays | 70% | 3 | 2.1 | Buffer time, Pair Programming, Code Reviews | Patrick
Bad Code | Violation of Clean Code principles, bad maintainability / expandability | 95% | 8 | 7.6 | Clean Code agent | Adrian
Bad communication | Insufficient requirements specifications | 35% | 9 | 3.15 | Clear instructions, Pair Programming, Sprint planning | Nikolas
Performance problems | e.g. generation algorithm | 15% | 2 | 0.3 | Performance optimization | Adrian
Unity specific Monobehavior class | Object orientation becomes harder | 5% | 1 | 0.05 | Get used to this Concept | all
Inexperience with utilized IDE | Shortcuts are different than in the IDE we are used to, which makes developing less efficient | 40% | 2 | 0.8 | Shortcut List for VisualStudio | Patrick
0
0
0
0
0
0
0
0
0
0
0
0
0